## Individual
Team members Name | Task completed | File Name | Purpose of function/model/document | Estimated time for task | Actual time taken for task
Zack Cornfield | Renderer (use GLFW facade) | Renderer.cpp, Renderer.h | Render Buffers | 20min | 20min
Zack Cornfield | Shader (Use GLFW facade) | Shader.cpp, Shader.h | Provide Shader Functionality | 20min | 20min
Zack Cornfield, Jacob Mondi | Graphics Utility (Facade of GLFW) | GraphicsUtility.cpp, GraphicsUtility.h | Façade of GLFW | 2hr | 3hr 30min
Zack Cornfield | Buffer Classes (use GLFW facade) | Buffer Files… |  | 40min | 40min
Thomas Stiles | Scripting Engine | Scripting.cpp, Scripting.h | Scripting Functionality | 3hr | 5hr
Zack Cornfield | TextureManager | TextureManager.cpp, TextureManager.h | Manages/Stores Textures within engine | 1hr | 1hr
Zack Cornfield | Time | Time.cpp, Time.h | Provide Time Functionality | 40min | 40min
Zack Cornfield | Simple Terrain Engine | Terrain.cpp, Terrain.h | Provide a simple terrain engine (loads heightmaps, generate terrain) | 3hr | 4hr
Zack Cornfield | Image | Image.cpp, Image.h | Façade of stb_image | 1hr | 1hr 30min
Zack Cornfield, Milad | UI (Revamp and Facade) | UI.cpp, UI.h | Façade of ImGUI | 1hr | 1hr
Zack Cornfield, Milad, Thomas Stiles | MeshRenderer | MeshRenderer.cpp, MeshRenderer.h | Render entities (set shader uniforms, bind textures, call render class etc.) | 2hr | 5hr
Thomas Stiles | GitHub Repository |  |  | 20min | 20min
Thomas Stiles | Cmake |  |  | 3hr | 1day
Milad | Trello |  |  | 20min | 20min
Thomas Stiles, Milad, Jacob Mondi | Setup Project |  |  | 1hr | 1hr
Jacob Mondi, Milad | glm facade |  | Façade of GLM | 1hr | 1hr 30min
Milad | Physics | Physics.h, Physics.cpp | Provide Physics Functionality | 5hr | 5hr
Thomas Stiles | ENTT | ECS.h | Entity Component System | 6hr | 8hr
Thomas Stiles | Component | Component.h, Component.cpp | Entity Components | 50min | 50min
Milad | MeshLoader (ASSIMP) | MeshLoader.cpp, MeshLoader.h | Loads Meshes using ASSIMP | 4hr | 4hr
Milad, Jacob Mondi | Input Handler | InputHandler.cpp, InputHandler.h | Provides Input Handling functionality | 1hr | 3hr
Milad | Adding Extra GLM Facade functionality |  |  | 3hr | 3hr
Milad | Changing glm in files to data structures |  |  | 4hr | 4hr
Milad | bat file |  |  | 30min | 30min
Zack Cornfield | TextureGenerator | TextureGenerator.cpp, TextureGenerator.h |  | 1hr | 1hr
Zack Cornfield | TextureManager Extra Work | TextureManager.cpp, TextureManager.h |  | 1hr | 1hr
Zack Cornfield | Texture Blending and Detail Map | Terrain.cpp, Terrain.h |  | 3hr | 3hr
Zack Cornfield | Skybox | Skybox.cpp, Skybox.h |  | 4hr | 6hr
Zack Cornfield | UI Fixes/Testing | UI.cpp, UI.h |  | 2hr | 2hr
Zack Cornfield | Finding/Creating Models |  |  | 1hr 30min | 1hr 30min
Jacob, Thomas | Terrain Lighting/Shaders |  |  | 1hr | 2hr
Jacob Mondi | CLOD | Terrain.cpp, Terrain.h |  | 8hr | 8hr
Jacob Mondi | Creating HeightMap |  |  | 1hr | 1hr
Milad | Creating Vacuum Model |  |  | 30min | 30min
Zack, Milad, Thomas, Jacob | Creating Game with scripts |  |  | 5hr | 5hr
Zack Cornfield | Individual Accounting |  |  | 30min | 30min
Zack Cornfield | User Manual |  |  | 30min | 30min
Zack Cornfield | Group Declaration Sheet |  |  | 20min | 20min
Zack Cornfield | TaskBreakdownList |  |  | 10min | 10min
Zack Cornfield, Milad | Discussion of Issues |  |  | 25min | 25min
Zack Cornfield, Jacob Mondi, Thomas Stiles | Game Design Document |  |  | 3hr | 3hr
Milad, Jacob Mondi | Group Self Assessment |  |  | 40min | 40min